## Gantt Data
Task | Start Month | Duration (Months) | Offset for Gantt
Project Planning | 1 | 1 | 0
Requirements Analysis | 1 | 2 | 0
Solution Design | 2 | 2 | 1
Prototype Development | 3 | 2 | 2
Prototype Refinement | 4 | 2 | 3
Testing & Evaluation | 5 | 1 | 4
Privacy & Risk Review | 5 | 1 | 4
Final Report & Recommendations | 6 | 1 | 5

## Timeline View
Task | M1 | M2 | M3 | M4 | M5 | M6
Project Planning | bar: M1
Requirements Analysis | bar: M1 to M2
Solution Design | bar: M2 to M3
Prototype Development | bar: M3 to M4
Prototype Refinement | bar: M4 to M5
Testing & Evaluation | bar: M5
Privacy & Risk Review | bar: M5
Final Report & Recommendations | bar: M6

## Notes
6-Month Gantt Chart Workbook
This workbook contains the same 6-month Gantt structure as your screenshot.
Use the Gantt Data sheet to edit tasks, start month and duration.
Use the Timeline View sheet for an Excel-friendly visual timeline.
To create a stacked bar chart in Excel from Gantt Data:
1. Select columns A, D and C in the Gantt Data sheet.
2. Insert -> Bar Chart -> Stacked Bar.
3. Set the Offset series to No Fill.
4. Reverse category order on the vertical axis.
5. Set the horizontal axis minimum to 0 and maximum to 6.
6. Rename axis labels to M1-M6 if needed.